## Coordination Report
Consultant Villa Visual Report
Model Name |  |  | 2025-03-12_Full Villa Model Training_v4 Version: 9.13
Checker |  |  | ccollucci@windover.com
Organization |  |  | Windover Construction
Date |  |  | 2025-05-09 08:41
Full Villa Model_021424 |  |  | Date: 2024-02-14 13:57:45-05:00 Application: Autodesk Revit 2024 (ENU) IFC: IFC2X3
Villa MEP |  |  | Date: 2023-09-11 13:49:35 Application: Autodesk Revit 2021 (ENU) IFC: IFC2X3
Villa Training Model Presentation Report
Number | Id | Location | Date | Issue Title | Picture | Issue Description | Status
1 | 70 | (Arch) Top of Parapet, (Arch) Ground Floor, (Arch) Finish Pavement, (Arch) First Floor, (Arch) Roof Deck | 2025-05-09 08:40 | Title |  |  | Open
2 | 43 | (Arch) Ground Floor Lobby[7], Storage[15], Lobby[26] | 2024-02-29 08:01 | Stair.0.1 Clearance at Beginning of Stair |  | 1009 Stairways 1009 Stairways. In order to be considered part of an accesible means of egress, an exit access stair way as permitted by Section 1016.1 or exit stairway shall have a clear width of 1.2 m minimum between handrails and shall either incorporate an area of refuge within an enlarged floor-level landing or shall be accessed from either an area of refuge complying with Section 1007.6 or a horizontal exit.Exceptions:1. The area of refuge is not required at open exit access or exit stair ways as permitted by Sections 1016.1 and1022.1 in buildings that are equipped through out with an automatic sprinkler system installed in accordance with Section 903.3.1.1 or 903.3.1.2.2. The clear width of 1.2 m between handrails is not required at exit access stair way as permitted by Section 1016.1or exit stairways in buildings equipped through out with an automatic sprinkler system installed in accordance with Section 903.3.1.1 or 903.3.1.2.3. Areas of refuge are not required at exit stairways in buildings equipped through out with an automatic sprinkler system installed in accordance with Section 903.3.1.1 or 903.3.1.2.4. The clear width of 1.2 m between hand rails is not required for exit stair ways accessed from a horizontal exit.5. Areas of refuge are not required at exit stair ways serving open parking garages.6. Areas of refuge are not required for smoke protected seating areas complying with Section 1028.6.2.7. The areas of refuge are not required in Group R-2 occupancies. Stair (Arch) Stair.0.1 Not enough space at the beginning of (Arch) Stair.0.1.<br/> - Component (Arch) Door.0.7 intersects the required free area with dimensions 310 mm and 200 mm.<br/> - (Arch) Wall.0.57 intersects the required free area in 2 locations: with dimensions 310 mm and 200 mm 1.00 m and 200 mm<br/> - (Arch) Wall.0.22 intersects the required free area in 4 locations: with dimensions 310 mm and 200 mm 1.00 m and 200 mm 1.00 m and 5 mm 150 mm and 50 mm | Open
3 | 44 | (Arch) Ground Floor Lobby[7], Storage[15], Lobby[26] | 2024-02-29 08:03 | Stair.0.1 Handrail Extension too Short |  | 1009 Stairways 1009 Stairways. In order to be considered part of an accesible means of egress, an exit access stair way as permitted by Section 1016.1 or exit stairway shall have a clear width of 1.2 m minimum between handrails and shall either incorporate an area of refuge within an enlarged floor-level landing or shall be accessed from either an area of refuge complying with Section 1007.6 or a horizontal exit.Exceptions:1. The area of refuge is not required at open exit access or exit stair ways as permitted by Sections 1016.1 and1022.1 in buildings that are equipped through out with an automatic sprinkler system installed in accordance with Section 903.3.1.1 or 903.3.1.2.2. The clear width of 1.2 m between handrails is not required at exit access stair way as permitted by Section 1016.1or exit stairways in buildings equipped through out with an automatic sprinkler system installed in accordance with Section 903.3.1.1 or 903.3.1.2.3. Areas of refuge are not required at exit stairways in buildings equipped through out with an automatic sprinkler system installed in accordance with Section 903.3.1.1 or 903.3.1.2.4. The clear width of 1.2 m between hand rails is not required for exit stair ways accessed from a horizontal exit.5. Areas of refuge are not required at exit stair ways serving open parking garages.6. Areas of refuge are not required for smoke protected seating areas complying with Section 1028.6.2.7. The areas of refuge are not required in Group R-2 occupancies. Stair (Arch) Stair.0.1 Handrail of the (Arch) Stair.0.1 is not extended enough: 50 mm. The minimum extended length for the handrail is 305 mm. | Open
4 | 45 | (Arch) Ground Floor Lobby[7], Storage[15], Lobby[26] | 2024-02-28 20:31 | Stair.0.1: Head Clearance |  | 1009 Stairways 1009 Stairways. In order to be considered part of an accesible means of egress, an exit access stair way as permitted by Section 1016.1 or exit stairway shall have a clear width of 1.2 m minimum between handrails and shall either incorporate an area of refuge within an enlarged floor-level landing or shall be accessed from either an area of refuge complying with Section 1007.6 or a horizontal exit.Exceptions:1. The area of refuge is not required at open exit access or exit stair ways as permitted by Sections 1016.1 and1022.1 in buildings that are equipped through out with an automatic sprinkler system installed in accordance with Section 903.3.1.1 or 903.3.1.2.2. The clear width of 1.2 m between handrails is not required at exit access stair way as permitted by Section 1016.1or exit stairways in buildings equipped through out with an automatic sprinkler system installed in accordance with Section 903.3.1.1 or 903.3.1.2.3. Areas of refuge are not required at exit stairways in buildings equipped through out with an automatic sprinkler system installed in accordance with Section 903.3.1.1 or 903.3.1.2.4. The clear width of 1.2 m between hand rails is not required for exit stair ways accessed from a horizontal exit.5. Areas of refuge are not required at exit stair ways serving open parking garages.6. Areas of refuge are not required for smoke protected seating areas complying with Section 1028.6.2.7. The areas of refuge are not required in Group R-2 occupancies. Stair (Arch) Stair.0.1: 1.76 m The head clearance height above the stair (Arch) Stair.0.1 is 1.76 m. The minimum height for the stairs is 2.05 m. | Open
5 | 46 | (Arch) Ground Floor Lobby[26], Lobby[7], Storage[15] | 2024-02-29 08:04 | Stair.0.1 Handrail Too High |  | 1009 Stairways 1009 Stairways. In order to be considered part of an accesible means of egress, an exit access stair way as permitted by Section 1016.1 or exit stairway shall have a clear width of 1.2 m minimum between handrails and shall either incorporate an area of refuge within an enlarged floor-level landing or shall be accessed from either an area of refuge complying with Section 1007.6 or a horizontal exit.Exceptions:1. The area of refuge is not required at open exit access or exit stair ways as permitted by Sections 1016.1 and1022.1 in buildings that are equipped through out with an automatic sprinkler system installed in accordance with Section 903.3.1.1 or 903.3.1.2.2. The clear width of 1.2 m between handrails is not required at exit access stair way as permitted by Section 1016.1or exit stairways in buildings equipped through out with an automatic sprinkler system installed in accordance with Section 903.3.1.1 or 903.3.1.2.3. Areas of refuge are not required at exit stairways in buildings equipped through out with an automatic sprinkler system installed in accordance with Section 903.3.1.1 or 903.3.1.2.4. The clear width of 1.2 m between hand rails is not required for exit stair ways accessed from a horizontal exit.5. Areas of refuge are not required at exit stair ways serving open parking garages.6. Areas of refuge are not required for smoke protected seating areas complying with Section 1028.6.2.7. The areas of refuge are not required in Group R-2 occupancies. Stair: 190mm max riser 250mm going/Handrail too high (Arch) Stair.0.1 Handrail height is 1.10 m. The maximum allowed height for the handrail is 965 mm. | Open
6 | 47 | (Arch) Finish Pavement Sitting Room[1] | 2024-02-29 08:05 | Insufficient handrails at Ramp |  | 1010 Ramps If one of the occupants is a Person of Determination using wheelchairs or mobility aids, the following conditions for accessibility ramps must be met as part of emergency escape routes:A. 60% of the main entrances to the villa building must be provided with easy access ramps. B. The slope inclination ratio must be at least 12 horizontal meters per vertical meter. C. The vertical height of any slope must not exceed 76 cm. D. If the vertical height exceeds the distance specified in the previous item, a landing platform with a width not less than the slope's largest width and a length not less than 1.5 meters must be provided. E. The minimum slope width must be no less than 1.1 meters. F. Slopes or parts thereof must not extend outside the plot boundaries, except for the protrusion permitted in Article (6) of this Guide. Ramp: Ramp 1/Insufficient handrails | Open
7 | 48 | (Arch) Finish Pavement Sitting Room[1] | 2024-02-29 08:05 | Not Enough Space at End of Ramp |  | 1010 Ramps If one of the occupants is a Person of Determination using wheelchairs or mobility aids, the following conditions for accessibility ramps must be met as part of emergency escape routes:A. 60% of the main entrances to the villa building must be provided with easy access ramps. B. The slope inclination ratio must be at least 12 horizontal meters per vertical meter. C. The vertical height of any slope must not exceed 76 cm. D. If the vertical height exceeds the distance specified in the previous item, a landing platform with a width not less than the slope's largest width and a length not less than 1.5 meters must be provided. E. The minimum slope width must be no less than 1.1 meters. F. Slopes or parts thereof must not extend outside the plot boundaries, except for the protrusion permitted in Article (6) of this Guide. Ramp: Ramp 1/Not Enough Space at End | Open
8 | 49 | (Arch) First Floor, (Arch) Finish Pavement | 2024-02-28 20:34 | Roof.1.1 Roof Parapet Wall Heights Too Low |  | 10.13 Roof Floor Parapet Height A barrier must be constructed to enclose any unbuilt area of the roof floor, as well as the top roof of the roof floor, with a height not more than 2 meters (2.00 m) and not less than 1.20 meters (1.20 m). This barrier may be omitted on the upper roof of the roof floor if the area is unused and free of services, or if there is no staircase for access. (Arch) First Floor/Components too close (Arch) Roof.1.1 There are 4 component(s) in "(Arch) First Floor" too close to "(Arch) Roof.1.1". The minimum distance is 1.20 m. - (Arch) Wall.-1.10 Distance: 485 mm - (Arch) Wall.-1.17 Distance: 485 mm - (Arch) Wall.-1.11 Distance: 485 mm - (Arch) Wall.-1.6 Distance: 485 mm (Arch) Roof.1.2 There are 6 component(s) in "(Arch) First Floor" too close to "(Arch) Roof.1.2". The minimum distance is 1.20 m. - (Arch) Wall.-1.5 Distance: 390 mm - (Arch) Wall.-1.9 Distance: 390 mm - (Arch) Wall.-1.8 Distance: 390 mm - (Arch) Wall.-1.18 Distance: 855 mm - (Arch) Wall.-1.7 Distance: 855 mm - (Arch) Wall.-1.15 Distance: 855 mm | Open
9 | 50 | (Arch) First Floor, (Arch) Finish Pavement Sitting Room[1], Family Hall[25], Room[5] | 2024-02-28 20:33 | Roof.1.3 Parapet Height Too Low |  | 10.13 Roof Floor Parapet Height A barrier must be constructed to enclose any unbuilt area of the roof floor, as well as the top roof of the roof floor, with a height not more than 2 meters (2.00 m) and not less than 1.20 meters (1.20 m). This barrier may be omitted on the upper roof of the roof floor if the area is unused and free of services, or if there is no staircase for access. (Arch) First Floor/Components too close (Arch) Roof.1.3 There are 2 component(s) in "(Arch) First Floor" too close to "(Arch) Roof.1.3". The minimum distance is 1.20 m. - (Arch) Wall.-1.46 Distance: 750 mm - (Arch) Wall.-1.44 Distance: 750 mm | Open
10 | 51 | (Arch) First Floor, (Arch) Finish Pavement | 2024-02-28 20:34 | Roof.1.4 Parapet Roof Walls Too Low |  | 10.13 Roof Floor Parapet Height A barrier must be constructed to enclose any unbuilt area of the roof floor, as well as the top roof of the roof floor, with a height not more than 2 meters (2.00 m) and not less than 1.20 meters (1.20 m). This barrier may be omitted on the upper roof of the roof floor if the area is unused and free of services, or if there is no staircase for access. (Arch) First Floor/Components too close (Arch) Roof.1.4 There are 4 component(s) in "(Arch) First Floor" too close to "(Arch) Roof.1.4". The minimum distance is 1.20 m. - (Arch) Wall.-1.88 Distance: 464 mm - (Arch) Wall.-1.87 Distance: 464 mm - (Arch) Wall.-1.89 Distance: 464 mm - (Arch) Wall.-1.86 Distance: 464 mm | Open
11 | 52 | (Arch) Roof Deck, (Arch) First Floor, (Arch) Finish Pavement, (Arch) Ground Floor | 2024-02-28 20:35 | Main Villa Roof.2.1 Parapet Walls Too Low |  | 10.13 Roof Floor Parapet Height A barrier must be constructed to enclose any unbuilt area of the roof floor, as well as the top roof of the roof floor, with a height not more than 2 meters (2.00 m) and not less than 1.20 meters (1.20 m). This barrier may be omitted on the upper roof of the roof floor if the area is unused and free of services, or if there is no staircase for access. (Arch) Roof Deck/Components too close (Arch) Roof.2.1 There are 16 component(s) in "(Arch) Roof Deck" too close to "(Arch) Roof.2.1". The minimum distance is 1.20 m. - (Arch) Wall.1.17 Distance: 1.10 m - (Arch) Wall.1.12 Distance: 1.10 m - (Arch) Wall.1.14 Distance: 1.10 m - (Arch) Wall.1.6 Distance: 1.10 m - (Arch) Wall.1.3 Distance: 1.10 m - (Arch) Wall.-1.40 Distance: 1.10 m - (Arch) Wall.-1.47 Distance: 1.10 m - (Arch) Wall.-1.43 Distance: 1.10 m - (Arch) Wall.-1.53 Distance: 1.10 m - (Arch) Wall.0.9 Distance: 1.10 m - (Arch) Wall.-1.63 Distance: 1.10 m - (Arch) Wall.0.11 Distance: 1.10 m - (Arch) Wall.1.5 Distance: 1.10 m - (Arch) Wall.-1.42 Distance: 1.10 m - (Arch) Wall.0.44 Distance: 1.10 m - (Arch) Wall.-1.50 Distance: 1.10 m | Open
12 | 53 | (Arch) Ground Floor Bathroom[17] | 2024-02-28 20:37 | Bathroom Does Not Meet Minimum SF |  | 11.15 Element Space Area This rule checks that area of specified spaces is inside set limits. Too Small Spaces/Bathroom | Open
13 | 54 | (Arch) Ground Floor | 2024-02-28 20:47 | Car Port Canopy Height Min Height |  | 15.2.V Car Entrance Canopy Height Min The minimum height of the car entrance canopy should be four and a half meters (4.50 m). (Arch) Ground Floor | Open
14 | 55 | (Arch) Finish Pavement, (Arch) Ground Floor Hall[23] | 2024-02-28 20:53 | External Door Width Does Not Meet Min |  | 18.1 Primary Entrance Opening The primary entrance to the residential villa shall maintain a minimum width of one meter and twenty centimeters (1.20 meters). It is requisite that this entrance directrly opens into a living space. 0700mm x 2100mm Wrong value of Property - Width: 700 mm Door component(s) have wrong value. The actual value of Property: Width is 700 mm. ≥ 1.20 m. | Open
15 | 56 | (Arch) Finish Pavement | 2024-02-28 20:53 | Exterior Door Does Not Meet Min Height & Width Requirements |  | 18.1 Primary Entrance Opening The primary entrance to the residential villa shall maintain a minimum width of one meter and twenty centimeters (1.20 meters). It is requisite that this entrance directrly opens into a living space. 0800mm x 1700mm | Open
16 | 57 | (Arch) Ground Floor | 2024-02-28 20:54 | Interior Doors Do Not Meet Minimum Requirements |  | 1008.1.1 Size of Doors 1008.1.1 Size of doors. The minimum width of each door opening shall be suf fi cient for the occu pant load thereof and shall provide a clear width of 815 mm. Clear openings of doorways with swinging doors shall be measured between the face of the door and the stop, with the door open 90°. Where this section requires a minimum clear width of 815 mm and a door opening includes two door leaves without a mullion, one leaf shall provide a clear open ing width of 815 mm. The maximum width of a swinging door leaf shall be 1.2 m nominal. Means of egress doors in a Group I-2 occupancy used for the move ment of beds shall provide a clear width not less than 1.05 m. The height of door openings shall not be less than 2.05 m. Exceptions:1. The minimum and maximum width shall not apply to door open ings that are not part of the required means of egress in Group R-2 and R-3 occupancies.2. Door openings to resident sleeping units in Group I-3 occupancies shall have a clear width of not less than 710 mm. 3. Door open ings to storage closets less than 0.93 m2 in area shall not be lim ited by the minimum width. 4. Width of door leaves in revolving doors that comply with Section 1008.1.4.1 shall not be limited. 5. Door openings within a dwelling unit or sleeping unit shall not be less than 2 m in height. 6. Exterior door openings in dwelling units and sleeping units, other than the required exit door, shall not be less than 1.95 m in height. 7. In other than Group R-1 occupancies, the minimum widths shall not apply to interior egress doors within a dwelling unit or sleep ing unit that is not required to be an Accessible unit, Type A unit or Type B unit. 8. Door openings required to be accessible within Type B units shall have a minimum clear width of 805 mm. 0700mm x 2100mm/0800mm x 1700mm/0920 x 1700mm/0920 x 2160 mm/Garbage | Open
17 | 58 | (Arch) First Floor Dining[9], Toilet[21], Laundry[14], Terrace[10], Maid Room[16], Kitchen[12], Hall[20], Hall[3], Living Room[11], Bathroom[17], Lobby[7], Elec.[24], Hall[23], Toilet[22], Room[5], Foyer[2], Sitting Room[1], Hall[8], Storage[13], Bathroom[6] | 2024-02-28 20:57 | Guradrails Dot Not Meet Min Height Requirement |  | Guardrail Heights Guardrails must be no less than one point zero five meters (1.05m) high, measured vertically above the adjacent walking surfaces. (Arch) First Floor | Open
18 | 59 | (Arch) Ground Floor | 2024-02-28 20:58 | Car Port Ceiling Height Too Low |  | 20.4 Interior Annex Ceiling Heights (Car Port) Annex construction is permissible up to a single ground floor, with a height not exceeding six meters (6.00 meters) from the road axis level. For hospitality annexes erected outside the setback area, an increment of 0.5 meters in height is allowable for every 2 meters in annex length, up to a ceiling of 8.00 meters. (Arch) Ground Floor | Open
19 | 60 | (Arch) First Floor, (Arch) Ground Floor | 2024-02-28 20:58 | Service Block Ceiling Height Too Low |  | 20.4 Interior Annex Ceiling Heights (Service Block) Annex construction is permissible up to a single ground floor, with a height not exceeding six meters (6.00 meters) from the road axis level. For hospitality annexes erected outside the setback area, an increment of 0.5 meters in height is allowable for every 2 meters in annex length, up to a ceiling of 8.00 meters. (Arch) Ground Floor | Open
20 | 61 | (Arch) Finish Pavement | 2024-02-28 20:58 | Utility Room Ceiling Height Too Low |  | 20.4 Interior Annex Ceiling Heights (Utility Room) Annex construction is permissible up to a single ground floor, with a height not exceeding six meters (6.00 meters) from the road axis level. For hospitality annexes erected outside the setback area, an increment of 0.5 meters in height is allowable for every 2 meters in annex length, up to a ceiling of 8.00 meters. (Arch) Finish Pavement | Open
21 | 62 | (Arch) First Floor Master Bedroom[33], Sitting Room[1] | 2024-02-28 20:59 | Floor Slabs Not Thick Enough |  | 1910 Slab Thickness Floor slabs must be at least 89mm thick. Generic 80mm | Open
22 | 63 | (Arch) Finish Pavement Dining[9] | 2024-02-28 21:00 | Wall Foundation Footings Do Not Meet Min Requirements |  | 1809.4 Footings 1809.4 Depth and width of footings. The minimum depth of footings below the undisturbed ground surface shall be 305 mm. Where applicable, the require ments of Section 1809.5 shall also be satisfied. The minimum width of footings shall be 305 mm. Wall Foundation:Bearing Footing - 762x279/Wall Foundation:Bearing Footing - 762x304 | Open
23 | 66 | (MEP) Level 2 Bathroom[29], Family Hall[25], Lobby[26], Bedroom[39] | 2024-02-28 21:11 | Level 2 Fresh Air and Exhaust Ductowkr for ERV too close |  | HVAC 1.0 Air Duct Separation Distance A minimum clearance of 1 meter must be maintained between return and supply ductwork. (MEP) Level 2/Components too close (MEP) Duct.1.10 There are 9 component(s) in "(MEP) Level 2" too close to "(MEP) Duct.1.10". The minimum distance is 3.05 m. - (MEP) Duct.1.9 Distance: 873 mm | Open
24 | 64 | (MEP) Level 1 Lobby[7], Toilet[21], Maid Room[16], Kitchen[12], Storage[13], Bathroom[6] | 2024-02-28 21:10 | Ground Level Fresh Air Ductwork for ERV too close |  | HVAC 1.0 Air Duct Separation Distance A minimum clearance of 1 meter must be maintained between return and supply ductwork. (MEP) Level 1 | Open
25 | 67 | (Arch) Ground Floor Toilet[22] | 2024-02-29 08:07 | Intersections Between Hydronic Supply 2 and Mechanical Exhaust Air 1 |  | HVAC 3.0 MEP Components Clashes This rule checks intersections between MEP Discipline components excluding componenents specfied as Covering (Insulation) Intersections Between Hydronic Supply 2 and Mechanical Exhaust Air 1 | Open
26 | 68 | (Arch) First Floor Bedroom[39] | 2024-02-28 21:06 | Intersections Between Hydronic Supply 3 and Mechanical Exhaust Air 5 |  | HVAC 3.0 MEP Components Clashes This rule checks intersections between MEP Discipline components excluding componenents specfied as Covering (Insulation) Intersections Between Hydronic Supply 3 and Mechanical Exhaust Air 5/Intersections Between Hydronic Supply 4 and Mechanical Exhaust Air 5 | Open
27 | 65 | (MEP) Level 1 Lobby[7], Storage[13] | 2024-02-28 21:02 | Level 2 Fresh Air and Exhaust Ductowkr for ERV too close |  | HVAC 1.0 Air Duct Separation Distance A minimum clearance of 1 meter must be maintained between return and supply ductwork. (MEP) Level 1/Components too close (MEP) Duct.0.6 There are 3 component(s) in "(MEP) Level 1" too close to "(MEP) Duct.0.6". The minimum distance is 3.05 m. - (MEP) Duct.0.2 Distance: 877 mm | Open
28 | 69 | (Arch) First Floor Lobby[26] | 2024-02-28 21:06 | Intersections Between Hydronic Supply 5 and Mechanical Exhaust Air 5 |  | HVAC 3.0 MEP Components Clashes This rule checks intersections between MEP Discipline components excluding componenents specfied as Covering (Insulation) Intersections Between Hydronic Supply 5 and Mechanical Exhaust Air 5 | Open